## Sprints
Sprint | Week | Sprint Goal | Start Date | End Date | Sprint State
1 | 2/3 |  | 2024-10-24 | 2024-11-08 | Inactive
2 | 4/5 | Spliting the parts between the members | 2024-11-07 | 2024-11-18 | Closed
3 | 6/7 | Starting on the website for the library system Features planned to implement: •User Authentication •Sign in/Sign Up Features •HomePage for the website •Database Integration(Sqlite) | 2024-11-21 | 2024-12-02 | Closed
MST + Term Break
4 | 13 | Adding some main features to the website •Searching up for books •Selecting books •Borrowing books | 2025-01-06 | 2025-01-10 | Closed
5 | 14 | Starting on implementing hardware: •Testing barcode scanner •Testing rfid scanner | 2025-01-14 | 2025-01-17 | Closed
6 | 15/16 | Implement payment and book collection functionality Starting on implementing hardware: •Testing barcode scanner •Testing rfid scanner •Testing servo motor | 2025-01-20 | 2025-01-31 | Closed
7 | 17 | •Integrate LCD menu function •Develop userdashboard and improve book reservation and branch choosing functionality •Compile and integration tests | 3 Febraury 2025 | 7 Febraury 2025 | Closed
8 | 18/19 | •Final bug fixes •Container Deployment •Demo and documentation •Python Test Cases | 10 Febraury 2025 | 16 Febraury 2025 | Active
Formulas:
End Date = [Start Date]+15
Start Date = [Start Date, row above]+14

## Active Sprint Board (hidden)
To Do | Doing | Done

## Product Backlog
ID | Story Title | Story Description | Definition of Done | Estimated Effort (hours) | Actual Effort (hours) | Status | Sprint
1 | Create Use Case Diagrams in SRS document | As a Software Developer, I need to define all the different Use Case Diagrams for the Automated Checkout System | All necessary Use Case Diagrams are defined in the SRS document SRS document is commited and pushed to Github | 4 | 5 | To Do | Sprint 1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95 | [5 empty] | Doing
96
97
98
99
100

## enum (hidden)
Sprint | Start Date | End Date | Story Status | Spint State
Sprint 1 |  |  | To Do | Inactive
Sprint 2 |  |  | Doing | Active
Sprint 3 |  |  | Done | Closed
Sprint 4
Sprint 5
Sprint 6