## Sprints
Sprint | Week | Sprint Goal | Start Date | End Date | Sprint State
1 | 2/3 |  | 2024-10-24 | 2024-11-08 | Inactive
2 | 4/5 | Spliting the parts between the members | 2024-11-07 | 2024-11-18 | Closed
3 | 6/7 | Starting on the website for the library system Features planned to implement: •User Authentication •Sign in/Sign Up Features •HomePage for the website •Database Integration(Sqlite) | 2024-11-21 | 2024-12-02 | Closed
MST + Term Break
4 | 13 | Adding some main features to the website •Searching up for books •Selecting books •Borrowing books | 2025-01-06 | 2025-01-10 | Closed
5 | 14 | Starting on implementing hardware: •Testing barcode scanner •Testing rfid scanner | 2025-01-14 | 2025-01-17 | Closed
6 | 15/16 | Implement payment and book collection functionality Starting on implementing hardware: •Testing barcode scanner •Testing rfid scanner •Testing servo motor | 2025-01-20 | 2025-01-31 | Closed
7 | 17 | •Integrate LCD menu function •Develop userdashboard and improve book reservation and branch choosing functionality •Compile and integration tests | 3 Febraury 2025 | 7 Febraury 2025 | Closed
8 | 18/19 | •Final bug fixes •Container Deployment •Demo and documentation •Python Test Cases | 10 Febraury 2025 | 16 Febraury 2025 | Active
Formulas:
End Date = [Start Date]+15
Start Date = [Start Date, row above]+14

## Active Sprint Board (hidden)
To Do | Doing | Done

## Product Backlog
ID | Story Title | Story Description | Definition of Done | Estimated Effort (hours) | Actual Effort (hours) | Status | Sprint
1 | Create Use Case Diagrams in SRS document | As a Software Developer, I need to define all the different Use Case Diagrams for the Automated Checkout System | All necessary Use Case Diagrams are defined in the SRS document SRS document is commited and pushed to Github | 4 | 5 | Done | Sprint 1
2 | Develop System Architecture | As a Developer, I need to define the hardware components for implementation on Raspberry Pi. | System Architecture is document in SRS and includes hardware integration. | 1 | 2 | Done | Sprint 1
3 | Plan Functional Requirements | As a Developer, I need to define functional requirement for the project. | Functional requirements are categorized into sections and draw respective flowcharts. | 4 | 5 | Done | Sprint 2
4 | Plan Non-Functional Requirements | As a Developer, I need to define non-functional requirements for the system. | Performance, Security and Power Management for different functionality are included in Non-Functional requirements. | 4 | 5 | Done | Sprint 2
5 | Define Static Software Architecture | As a Developer, I need to define a static software architecture diagram to illustrate the system's modules and components. | Static Architecture is documented with diagrams. | 3 | 2 | Done | Sprint 2
6 | Implement User Authentication | As a User, I log in and authenticate with my credentials. | Users can sign up and fill credentials like FIN Number and Student ID. And users can sign in using email and password. | 4 | 3 | Done | Sprint 3
7 | Branch Selection ( Branch 1 and 2 ) | As a User, I need to select a branch so that I can see the book availability in the selected branch. | Users can choose between Branch 1 and Branch 2, and the book availability is updated based on the selected branch. | 5 | 7 | Done | Sprint 3
8 | Implement Home Page and View More | As a User, I need to view books on Home Page , and I need to view books categorized by genres on the View More Page. | The Home Page displays books and View More Page displays books organized into genres. | 6 | 5 | Done | Sprint 3
9 | Searching Books | As a User, I need to search for books by title, author or genre so that I can find the books I'm looking for. | The search functionality is implemented. | 1 | 2 | Done | Sprint 4
10 | Book Selection | As a User, I need to select books and see respective book information | After selecting a book, book information with title, author, genre, etc and its availability status are displayed. | 5 | 6 | Done | Sprint 4
11 | Borrowing Books | As a User, I need to borrow books. | Availability status is showed as Available or Unavailable. When a user borrowed, the book's status is updated to " Unavailable" for the chosen branch. | 4 | 5 | Done | Sprint 4
12 | Reserving Books | As a User, I need to confirm reservation for borrowing books. | In the reserved page, borrowing books are showed under respective branch and user can confirm reservation. | 6 | 8 | Done | Sprint 4
13 | Barcode Scanner Integration | As a User, I need to scan books using a barcode for easy returning system. | Barcode scanner integration is implemented and can be used to identify books returning system. | 5 | 4 | Done | Sprint 5
14 | RFID Scanner Integration | As a User, I need to scan card or RFID tag for fines payment. | RFID scanner reads card or tags for payment functionality. | 4 | 3 | Done | Sprint 5
15 | Servo Motor Integration | As a system, it needs to integrate the servo motor to dispense the books after successful authentication. | The servo motor function is implemented. | 4 | 3 | Done | Sprint 6
16 | LCD Menu Integration | As a User, I need to navigate the menu on a LCD screen to pay loans, collect and return books or exit. | LCD menu displays payable fines, instruction for collecting and returning books. | 4 | 5 | Done | Sprint 7
17 | User Dashboard | A a User, I need a dashboard that displays my borrowed books, payable fines, and my profile. | The user dashboard is designed, showing borrowed books, payable fines and personal info. | 3 | 4 | Done | Sprint 7
18 | Borrowed Books Page | As a User, I need to seen my reserved books and how many days left to return. | After reserving books, borrowed books can be seen on Borrowed Books Page. Remaining Days and can extend period. | 6 | 7 | Done | Sprint 7
19 | Ultrasonic Sensor Integration | As a system, it needs to start automatically the process of returning or collecting books when a book is placed near an ultrasonic sensor. | The ultrasonic sensor is integrated, and when a book is placed near it, the system triggers the return or collection process. | 5 | 4 | Done | Sprint 7
20 | Log out Implementation | As a User, I need to log out of the system so that my session ends securely. | Log out functionality is implemented. | 3 | 2 | Done | Sprint 7
21
22

## enum (hidden)
Sprint | Start Date | End Date | Story Status | Spint State
Sprint 1 |  |  | To Do | Inactive
Sprint 2 |  |  | Doing | Active
Sprint 3 |  |  | Done | Closed
Sprint 4
Sprint 5
Sprint 6